## Schedule V1.0 (hidden)
Como House Club21 Server Room Work Schedule V1.0
Day # | Man-Hour Forecast |  | Work Scope | Remark | Time
Day 1 | 8 Hours | Night/Weekend | Rack 10 - trace, re-patch, tidy up existing cable points Trace 7 existing cable points to work desk | Critical racks | 6am to 8am
Day 2 | 8 Hours | Office Hour | Rack 1 - trace, re-patch, tidy up existing cable points |  | before 1030am
Day 3 | 8 Hours | Office Hour | Rack 2 - trace, re-patch, tidy up existing cable points |  | before 1030am
Day 4 | 8 Hours | Office Hour | Rack 3 & 4 - trace, re-patch, tidy up existing cable points |  | Office hour
Day 5 | 8 Hours | Office Hour | Rack 5 & 6 - trace, re-patch, tidy up existing cable points Rack 6 - dismantle un-used servers/equipment |  | Office hour
Day 6 | 8 Hours | Office Hour | Rack 7 - trace, re-patch, tidy up existing cable points Rack 9 - dismantle equipment and rack disposal |  | Office hour
Day 7 | 8 Hours | Office Hour | Labelling |  | Office hour

## Rack Front View
Front View | Rack 10 |  |  | Rack 7 |  | Rack 6 |  |  | Rack 5 |  |  | Rack 4 |  |  | Rack 3 |  |  | Rack 2 |  |  | Rack 1
172.21.27.1 | Cisco Catalyst 3650 Backup Switch | 42 |  |  | 42 |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  | Cable Slot | 42
|  | 41 |  | Dell Force10 S55 FTOS 1 | 41 |  | 41 |  |  | 41 |  |  | 41 |  | Patch | 41 |  | Cable Slot | 41 |  | Patch Panel | 41
172.21.26.1 | Cisco Catalyst 3650 App Network | 40 |  |  | 40 |  | 40 |  |  | 40 | 192.168.5.191 | Lenovo System x3650 M5 (5462-IDB) | 40 |  | Panel | 40 |  | Patch Panel | 40 |  | Patch Panel | 40
|  | 39 |  | Dell Force10 S55 FTOS 2 | 39 |  | 39 | 192.168.17.3 | Dell EMC PowerEdge R350 VEEAMSVR | 39 |  | SGCLUB21FIN | 39 |  |  | 39 |  | Cable Slot | 39 |  | Cable Slot | 39
172.21.25.1 | Cisco Catalyst 3650 DB Network | 38 |  |  | 38 |  | 38 | 192.168.17.5 | Synology Rackstation RS1221RP+ | 38 | 192.168.5.10 & | Lenovo System x3650 M5 (8871-AC1) | 38 | G700 | Avaya G700 | 38 |  | Patch Panel | 38 |  | Patch Panel | 38
|  | 37 |  | Aruba 6000 R8N85A EDW 1 | 37 |  | 37 |  | NAS-M | 37 | 192.168.5.178 | SGCLUB21BI | 37 | MAIN G2 | Media Gateway | 37 |  | Patch Panel | 37 |  | Patch Panel | 37
192.168.100.36 | Cisco Catalyst 3650 M3 Production | 36 |  |  | 36 |  | 36 | 192.168.17.4 | Synology Rackstation RS1221RP+ | 36 | 192.168.5.13 | Lenovo System x3650 M5 (8871-AC1) | 36 | S8300/G700 | Avaya G700 | 36 |  | Cable Slot | 36 |  | Cable Slot | 36
|  | 35 |  | Aruba 6000 R8N85A EDW 2 | 35 |  | 35 |  | NAS-DW | 35 |  | SGCLUB21BK | 35 | MAIN G1 | Media Gateway | 35 |  | Patch Panel | 35 |  | Patch Panel | 35
|  | 34 |  |  | 34 |  | 34 | 192.168.5.25 |  | 34 | 192.168.5.102 | Lenovo System x3650 M5 (8871-AC1) | 34 |  |  | 34 |  | Cable Slot | 34 |  | Patch Panel | 34
|  | 33 |  |  | 33 |  | 33 | 192.168.5.185 |  | 33 |  | SG-C21-SV-00004 | 33 | G700 | Avaya G700 | 33 |  | Patch Panel | 33 |  | Cable Slot | 33
|  | 32 |  |  | 32 |  | 32 | 192.168.5.24 |  | 32 | 192.168.5.22 | IBM System x3630 M3 (7377-42A) | 32 | LSP-A G4 | Media Gateway | 32 |  | Patch Panel | 32 |  | Patch Panel | 32
192.168.5.93 | Dell EMC PowerEdge R340 | 31 |  |  | 31 |  | 31 | 192.168.5.94 |  | 31 |  | SGCLUB21RICOH | 31 | S8300/G700 | Avaya G700 | 31 |  | Cable Slot | 31 |  | Patch Panel | 31
|  | 30 |  |  | 30 |  | 30 |  |  | 30 |  |  | 30 | LSP-A G3 | Media Gateway | 30 |  | Patch Panel | 30 |  | Cable Slot | 30
192.168.5.4 | Synology Rackstation RS2418+ | 29 |  |  | 29 |  | 29 |  |  | 29 |  |  | 29 |  |  | 29 |  |  | 29 | 192.168.100.21 | Aruba 6100 JL675A | 29
|  | 28 |  |  | 28 |  | 28 |  |  | 28 |  |  | 28 | G700 | Avaya G700 | 28 |  |  | 28 |  | Cable Slot | 28
| IBM 7316-TF3 KVM LCD Monitor | 27 |  |  | 27 |  | 27 | - |  | 27 |  |  | 27 | LSP-B G6 | Media Gateway | 27 |  | Cable Slot | 27 | 192.168.100.22 | Aruba 6100 JL675A | 27
192.168.5.33 | Lenovo System x3650 M5 (5462-AC1) | 26 |  |  | 26 |  | 26 |  |  | 26 |  |  | 26 | S8300/G700 | Avaya G700 | 26 |  |  | 26 |  | Cable Slot | 26
| SGCLUB21M3ADM | 25 |  |  | 25 |  | 25 |  |  | 25 |  |  | 25 | LSP-B G5 | Media Gateway | 25 |  |  | 25 | 192.168.100.23 | Aruba 6100 JL675A | 25
192.168.5.32 | Lenovo System x3650 M5 (5462-AC1) | 24 |  |  | 24 |  | 24 |  |  | 24 |  |  | 24 |  |  | 24 |  | Cable Slot | 24 |  | Cable Slot | 24
| SGCLUB21M3DBAUX | 23 |  |  | 23 |  | 23 |  |  | 23 |  |  | 23 |  |  | 23 | 192.168.100.31 | Aruba 6100 JL675A | 23 | 192.168.100.24 | Aruba 6100 JL675A | 23
192.168.5.35 | Lenovo System x3650 M5 (5462-AC1) | 22 |  |  | 22 |  | 22 |  |  | 22 |  |  | 22 |  |  | 22 |  | Cable Slot | 22 |  | Cable Slot | 22
| SGCLUB21M3ISO | 21 |  |  | 21 |  | 21 |  |  | 21 |  |  | 21 |  |  | 21 | 192.168.100.32 | Aruba 6100 JL675A | 21 |  |  | 21
|  | 20 | 192.168.155.14 | Dell EMC PowerEdge R740xd | 20 |  | 20 |  |  | 20 | 192.168.5.47 | Dell EMC Unity XT | 20 |  |  | 20 |  | Cable Slot | 20 |  |  | 20
|  | 19 |  | CLD-DB | 19 |  | 19 |  |  | 19 |  | CLUB21UNISTOR2 | 19 |  |  | 19 | 192.168.100.33 | Aruba 6100 JL675A | 19 |  |  | 19
|  | 18 | 192.168.155.13 | Dell EMC PowerEdge R740 | 18 |  | 18 | 192.168.5.38 | Lenovo System x3650 M5 (5462-IDD) | 18 | 192.168.5.46 | Dell EMC Unity XT | 18 |  |  | 18 |  | Cable Slot | 18 |  |  | 18
|  | 17 |  | CLD-APP | 17 |  | 17 |  | SGCLUB21M3IC | 17 |  | CLUB21UNISTOR1 | 17 |  |  | 17 | SNGGMNS9948938 | Cisco 4321 | 17 |  |  | 17
|  | 16 | 192.168.155.12 | Dell EMC PowerEdge R740xd | 16 |  | 16 | 192.168.5.98 | Lenovo System x3650 M5 (5462-AC1) | 16 |  |  | 16 |  |  | 16 |  |  | 16 | 192.168.5.222 |  | 16
|  | 15 |  | CLD-DB | 15 |  | 15 |  | SGCLUB21EBUDGET | 15 | 192.168.5.101 | Dell PowerEdge R720 | 15 |  |  | 15 |  |  | 15 |  |  | 15
|  | 14 | 192.168.155.11 | Dell EMC PowerEdge R740 | 14 |  | 14 | 192.168.5.39 | Lenovo System x3650 M5 (5462-IDB) | 14 |  | SG-C21-SV-00001 | 14 |  |  | 14 |  |  | 14 |  | Tyco | 14
192.168.5.36 | Supermicro 116-5 SGCLUB21M3DB | 13 |  | CLD-APP | 13 |  | 13 |  | SGCLUB21M3BIDB | 13 |  | Dell PowerEdge R520 | 13 |  |  | 13 |  |  | 13 |  | Digital Video Recorder | 13
192.168.5.40 | Lenovo System x3650 M5 (5462-AC1) | 12 | 192.168.155.10 | Dell EMC PowerEdge R740 | 12 |  | 12 | 192.168.5.31 | Lenovo System x3650 M5 (5462-D2A) | 12 |  | CCTV Server (Rocam) | 12 |  |  | 12 |  |  | 12 |  |  | 12
| SGCLUB21WEB | 11 |  | CLD-SP | 11 |  | 11 |  | SGCLUB21M3BI | 11 |  |  | 11 |  |  | 11 |  |  | 11 |  |  | 11
192.168.5.37 | Lenovo System x3650 M5 (5462-AC1) | 10 | 192.168.155.9 | Dell EMC PowerEdge R740xd | 10 |  | 10 |  | APC Smart-UPS 5000 | 10 |  |  | 10 | 192.168.5.201 |  | 10 |  |  | 10 |  |  | 10
| SGCLUB21M3BE | 9 |  | CLP-BACKUP | 9 |  | 9 |  | UPS3 | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9
192.168.5.236 | Lenovo System x3650 M5 (5462-IDB) | 8 |  | Dell EMC Data Domain | 8 |  | 8 |  |  | 8 | 192.168.5.84 | Eaton 9SX 5000 | 8 |  |  | 8 | 192.168.5.1 | Fortinet FortiGate 200F | 8 |  |  | 8
| SGCLUB21OLDM3DB | 7 |  |  | 7 |  | 7 |  |  | 7 |  | Rack4-UPS1 | 7 | 192.168.5.3 | Fortinet FortiGate 200F | 7 | 192.168.5.2 | Cisco Catalyst 3850 L3CORESW1 | 7 |  |  | 7
192.168.5.86 | APC AP9631 Smart-UPS RT 5000 XL | 6 |  |  | 6 |  | 6 |  |  | 6 |  |  | 6 | 192.168.5.8 | Cisco Catalyst 3650 L3CORESW2 | 6 |  |  | 6 |  |  | 6
| M3UPS-Top | 5 | 192.168.5.82 | Eaton 9SX 3000 | 5 |  | 5 |  | APC Smart-UPS 5000 | 5 |  | APC Smart-UPS 5000 | 5 |  |  | 5 |  |  | 5 |  |  | 5
|  | 4 |  | Rack7-UPS1 | 4 |  | 4 |  | UPS4 | 4 |  | UPS5 | 4 |  |  | 4 |  |  | 4 |  |  | 4
192.168.5.85 | APC AP9537SUM Smart-UPS SRT 5000 | 3 | 192.168.5.83 | Eaton 9SX 5000 | 3 |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3
| M3UPS-Bottom | 2 |  | Rack7-UPS2 | 2 |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2
|  | 1 |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
APC
Smart-UPS 3000
Dell Precision Tower 3620
192.168.16.101
Dell Precision 3440
192.168.5.196 (ComoClub)
Dell Optiplex 5080
192.168.5.197 (ComoClub)
USB Drive
Mac-POS Portal
Mac-Administrators
Cisco 3900 Series
SingTel Ethernet Router
Huawei Optix PTN 905B
GIE4805S
Huawei Optix PTN 910
sgposubuntu
security-HDNVR (CCTV PC)
Mac-File maker
Mac-MAC Update
ATEN KVM CL5708-ATA
Tower PC
tray
HP 1410-24G Switch
Dell Precision Tower 3620
192.168.16.101
security-HDNVR CCTV PC PC)
Huawei Optix PTN 905B
Patch Panel
ISA-ES1 8FE (Alcatel 1642EMC)
Cisco Catalyst 2960G Series
RansNet HSG-800
APC
Smart-UPS RT 3000
192.168.5.87
rack2ups
APC
Smart-UPS RT 3000
192.168.5.88
rack1ups
Dell Monitor
(for CCTV PC)
tray
tray
Cisco 5500 Wireless Controller
Ruckus ICX 7150-C12P
192.168.5.41 &
192.168.5.179
CLUB21MISBI
For SGCLUB21FIN Backup
Powered off
Powered off
Panasonic KX-NS300
PABX
Huawei Optix PTN 905A MUX
Patch Panel
Powered off
*UPS Alert!
*UPS Alert!
*UPS Alert!
Powered off
Powered off
Powered off
Powered off

## Rack Rear View
Rear View | Rack 1-R |  | Rack 2-R |  |  | Rack 3-R |  | Rack 4-R |  |  | Rack 5-R |  | Rack 6-R |  | Rack 7-R |  | Rack 10-R
|  | 42 |  | 42 |  |  | 42 |  | 42 |  |  | 42 |  | 42 |  | 42 |  | 42
|  | 41 |  | 41 |  |  | 41 |  | 41 |  |  | 41 |  | 41 |  | 41 |  | 41
|  | 40 |  | 40 |  |  | 40 |  | 40 |  |  | 40 |  | 40 |  | 40 |  | 40
|  | 39 |  | 39 |  |  | 39 |  | 39 |  |  | 39 |  | 39 |  | 39 |  | 39
|  | 38 |  | 38 | 192.168.5.9 |  | 38 |  | 38 |  |  | 38 |  | 38 |  | 38 |  | 38
|  | 37 |  | 37 |  |  | 37 |  | 37 |  |  | 37 |  | 37 |  | 37 |  | 37
|  | 36 |  | 36 |  |  | 36 |  | 36 |  |  | 36 |  | 36 |  | 36 |  | 36
|  | 35 |  | 35 |  |  | 35 |  | 35 |  |  | 35 |  | 35 |  | 35 |  | 35
|  | 34 |  | 34 |  |  | 34 |  | 34 |  |  | 34 |  | 34 |  | 34 |  | 34
|  | 33 |  | 33 |  |  | 33 |  | 33 |  |  | 33 |  | 33 |  | 33 |  | 33
|  | 32 |  | 32 |  |  | 32 |  | 32 |  |  | 32 |  | 32 |  | 32 |  | 32
|  | 31 |  | 31 |  |  | 31 |  | 31 | 192.168.5.74 |  | 31 |  | 31 |  | 31 |  | 31
|  | 30 |  | 30 |  |  | 30 |  | 30 |  |  | 30 |  | 30 |  | 30 |  | 30
|  | 29 |  | 29 |  |  | 29 |  | 29 |  |  | 29 |  | 29 |  | 29 |  | 29
|  | 28 |  | 28 |  |  | 28 |  | 28 |  |  | 28 |  | 28 |  | 28 |  | 28
|  | 27 |  | 27 |  |  | 27 |  | 27 |  |  | 27 |  | 27 |  | 27 |  | 27
|  | 26 |  | 26 |  |  | 26 |  | 26 |  |  | 26 |  | 26 |  | 26 |  | 26
|  | 25 |  | 25 |  |  | 25 |  | 25 |  |  | 25 |  | 25 |  | 25 |  | 25
|  | 24 |  | 24 |  |  | 24 | EMC DS6505B SAN Switch | 24 |  |  | 24 |  | 24 |  | 24 |  | 24
|  | 23 |  | 23 |  |  | 23 | EMC DS6505B SAN Switch | 23 |  |  | 23 |  | 23 |  | 23 |  | 23
|  | 22 |  | 22 |  |  | 22 |  | 22 |  |  | 22 |  | 22 |  | 22 |  | 22
|  | 21 |  | 21 |  |  | 21 |  | 21 |  |  | 21 |  | 21 |  | 21 |  | 21
|  | 20 |  | 20 |  |  | 20 |  | 20 |  |  | 20 |  | 20 |  | 20 |  | 20
|  | 19 |  | 19 |  |  | 19 |  | 19 |  |  | 19 |  | 19 |  | 19 |  | 19
|  | 18 |  | 18 |  |  | 18 |  | 18 |  |  | 18 |  | 18 |  | 18 |  | 18
|  | 17 |  | 17 |  |  | 17 |  | 17 |  |  | 17 |  | 17 |  | 17 |  | 17
|  | 16 |  | 16 |  |  | 16 |  | 16 |  |  | 16 |  | 16 |  | 16 |  | 16
|  | 15 |  | 15 |  |  | 15 |  | 15 |  |  | 15 |  | 15 |  | 15 |  | 15
|  | 14 |  | 14 |  |  | 14 |  | 14 |  |  | 14 |  | 14 |  | 14 |  | 14
|  | 13 |  | 13 |  |  | 13 |  | 13 |  |  | 13 |  | 13 |  | 13 |  | 13
|  | 12 |  | 12 |  |  | 12 |  | 12 |  |  | 12 |  | 12 |  | 12 |  | 12
|  | 11 |  | 11 |  |  | 11 |  | 11 |  |  | 11 |  | 11 |  | 11 |  | 11
|  | 10 |  | 10 |  |  | 10 |  | 10 |  |  | 10 |  | 10 |  | 10 |  | 10
|  | 9 |  | 9 |  |  | 9 |  | 9 |  |  | 9 |  | 9 |  | 9 |  | 9
|  | 8 |  | 8 |  |  | 8 |  | 8 |  |  | 8 |  | 8 |  | 8 |  | 8
|  | 7 |  | 7 |  |  | 7 |  | 7 |  |  | 7 |  | 7 |  | 7 |  | 7
|  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  | 6 |  | 6
|  | 5 |  | 5 |  |  | 5 |  | 5 |  |  | 5 |  | 5 |  | 5 |  | 5
|  | 4 |  | 4 |  |  | 4 |  | 4 |  |  | 4 |  | 4 |  | 4 |  | 4
|  | 3 |  | 3 |  |  | 3 |  | 3 |  |  | 3 |  | 3 |  | 3 |  | 3
|  | 2 |  | 2 |  |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2
|  | 1 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1
RansNet CMG-1500
SingTel ONR (ZTE)
Fujitsu Deskpower 2000
192.168.5.252
CLUB21-Project_Card
LaCrosse Temp Sensor
TX60U-IT
RansNet CMG-1500
HP ProCurve 1400-SG Switch
Cisco 1841
Fortigate 30B
Synology DS414
eglobalstation
APC
Smart-UPS RT 3000
192.168.5.89
JBAUPS
LaCrosse Gateway
GW-1000U
Powered off

## Loc & Specs
Rack | Slot | Height | IP Address | Hostname | Joined Domain? | UPS #1 | UPS #2 | Make & Model | S/No | OS Platform | Memory | Hard Disks | Remarks
1 | 29 | 1U | 192.168.100.21 | Network Switch |  | R1-UPS |  | Aruba 6100 JL675A
1 | 27 | 1U | 192.168.100.22 | Network Switch |  | R1-UPS |  | Aruba 6100 JL675A
1 | 25 | 1U | 192.168.100.23 | Network Switch |  | R1-UPS |  | Aruba 6100 JL675A
1 | 23 | 1U | 192.168.100.24 | Network Switch |  | R1-UPS |  | Aruba 6100 JL675A
1 | 16 | Standalone | 192.168.5.222 | HotSpot Gateway |  | R1-UPS |  | Ransnet HSG-800 |  |  |  |  | Guest Wifi Captive Portal
1 | 12 | 4U |  |  |  | R1-UPS |  | Tyco Digital Video Recorder
1 | 1 | Standalone | 192.168.5.87 | rack2ups |  |  |  | APC AP9630 | ZA1516011945 |  |  |  | Smart-UPS RT 3000 XL
1 | 1 | Standalone | 192.168.5.88 | rack1ups |  |  |  | APC AP9630 | ZA1516011943 |  |  |  | Smart-UPS RT 3000 XL
2 | 23 | 1U | 192.168.100.31 | Network Switch |  |  | R2-UPS | Aruba 6100 JL675A
2 | 21 | 1U | 192.168.100.32 | Network Switch |  |  | R2-UPS | Aruba 6100 JL675A
2 | 19 | 1U | 192.168.100.33 | Network Switch |  |  | R2-UPS | Aruba 6100 JL675A
2 | 17 | 1U |  |  |  |  | R2-UPS | Cisco 4321
2 | 16 | 1U |  |  |  |  | R2-UPS | ISA-ES1 8FE (Alcatel 1642EMC)
2 | 15 | 1U |  |  |  |  | R2-UPS | Cisco Catalyst 2960G Series
2 | 11 | 3U |  | SingTel Ethernet Router |  |  | R2-UPS | Cisco 3900 Series |  |  |  |  | Powered off
2 | 9 | 1U |  |  |  |  | R2-UPS | Cisco 5500 Wireless Controller |  |  |  |  | Powered off
2 | 8 | 1U | 192.168.5.1 | Fortigate Firewall |  | R1-UPS | R2-UPS | Fortinet FortiGate 200F
2 | 7 | 1U | 192.168.5.2 | L3CORESW1 |  |  | R2-UPS | Cisco Catalyst 3850
2 | 5 | 1U |  |  |  |  | R2-UPS | Huawei Optix PTN 910
2 | 4 | 1U |  |  |  |  | R2-UPS | GIE4805S
2 | 3 | 1U |  |  |  |  | R2-UPS | Huawei Optix PTN 905B
3 | 37 | 2U |  | G700 MAIN G2 |  |  | UPS-5 | Avaya G700 Media Gateway | 081604501484
3 | 35 | 2U |  | S8300/G700 MAIN G1 |  |  | UPS-5 | Avaya G700 Media Gateway | 081606405265
3 | 32 | 2U |  | G700 LSP-A G4 |  |  | UPS-5 | Avaya G700 Media Gateway | 081604501395
3 | 30 | 2U |  | S8300/G700 LSP-A G3 |  |  | UPS-5 | Avaya G700 Media Gateway | 081606405266
3 | 27 | 2U |  | G700 LSP-B G6 |  |  | UPS-5 | Avaya G700 Media Gateway | 081606405272
3 | 25 | 2U |  | S8300/G700 LSP-B G5 |  |  | UPS-5 | Avaya G700 Media Gateway | 081606405271
3 | 12 | 1U |  | Network Appliance |  |  | R2-UPS | Huawei Optix PTN 905A
3 | 10 | 2U | 192.168.5.201 |  |  |  | R2-UPS | Panasonic KX-NS300 |  |  |  |  | PABX for Dempsey restaurants and KL Office
3 | 8 | 1U |  | Network Switch |  |  | UPS-5 | Ruckus ICX 7150-C12P
3 | 7 | 1U | 192.168.5.3 | Fortigate |  | R2-UPS | UPS-5 | Fortinet FortiGate 200F |  |  |  |  | ASA Firewall
3 | 6 | 1U | 192.168.5.8 | L3CORESW2 |  |  | UPS-5 | Cisco Catalyst 3650
3 | 1 | Standalone | 192.168.16.101 | security-HDNVR |  |  | UPS-5 | Avigilon HDNVR | 48ZVGL2 | Windows Embedded Standard | 8 GB | 465 GB (C:, System) | CCTV PC
4 | 39 | 2U | 192.168.5.191 | SGCLUB21FIN | y | R4-UPS1 | UPS-5 | Lenovo System x3650 M5 | 06HGBLR | Windows Server 2012 R2 Standard | 8 GB | 270 GB (C:, System), 2 TB (D:, Data) | Finance File Server (EA2, FIN_RGL, FIN_SIN, FIN_WHSE, FINFD, LI, ComoDempsey)
4 | 37 | 2U | 192.168.5.10 | SGCLUB21BI | y | R4-UPS1 | UPS-5 | Lenovo 8871-AC1 | J33WM3P | Windows Server 2016 Standard | 128 GB | 550 GB (C:, 275 GB, D:, 275 GB) 1 TB (E:, Data) | System x3650 M5; New BI server; same PC as 192.168.5.178
4 | 35 | 2U | 192.168.5.13 | SGCLUB21BK | y | R4-UPS1 | UPS-5 | Lenovo 8871-AC1 | J33XW16 | Windows Server 2016 Standard | 32 GB | 270 GB (C: System), 80 TB (D:, 50 TB, E:, 30 TB) | Powered off (De-comm) System x3650 M5; Veritas Backup Server
4 | 33 | 2U | 192.168.5.102 | SG-C21-SV-00004 | y | R4-UPS1 | UPS-5 | Lenovo 8871-AC1 | J32CWCZ | Windows Server 2022 Standard | 32 GB | 930 GB (C:, 200 GB, D:, 730 GB) | System x3650 M5; Hyper-V Manager for SGCLUB21DC2V & SGCLUB21DSYNC1v
4 | 31 | 2U | 192.168.5.22 | SGCLUB21RICOH | y | R4-UPS1 | UPS-5 | IBM 7377-42A | 99A0636 | Windows Server 2008 R2 Standard | 24 GB | 270 GB (C:, 150 GB, E: 120 GB) 400 GB (D:, Data) | Powered off (server failure); Old Ricoh print server
4 | 19 | 2U | 192.168.5.47 | CLUB21UNISTOR2 | y | R4-UPS1 | UPS-5 | Dell EMC Unity XT |  | UnityOS v5.0.1.0.6.128 |  |  | Shared Drives
4 | 17 | 2U | 192.168.5.46 | CLUB21UNISTOR1 | y | R4-UPS1 | UPS-5 | Dell EMC Unity XT |  | UnityOS v5.0.1.0.6.128 |  |  | Shared Drives
4 | 14 | 2U | 192.168.5.101 | SG-C21-SV-00001 | y | R4-UPS1 | UPS-5 | Dell PowerEdge R720 | 41F2232 | Windows Server 2022 Standard | 256 GB | 558 GB (C:, 100 GB, D:, 458 GB) | Hyper-V Manager for SGCLUB21RICOH & SGCLUB21DC1
4 | 12 | 2U |  | ROCAM CCTV |  | PUB Direct |  | Dell PowerEdge R520 | 6KXBG42
4 | 6 | 3U | 192.168.5.84 | Rack4-UPS1 |  |  |  | Eaton 9SX 5000i | G200N32006 |  |  |  | Eaton UPS 5 kVA
5 | 39 | 1U | 192.168.17.3 | VEEAMSVR |  | UPS-3 | UPS-4 | Dell EMC PowerEdge R350 | 7ZV0C14 | Windows Server 2022 Standard | 32 GB | 445 GB (C:, System) | Veeam Backup Server
5 | 38 | 2U | 192.168.17.5 | NAS-M |  | UPS-3 | UPS-4 | Synology RS1221RP+ | 23B0RXR6BAVQE | DSM 7.2.1-69057 Update 4 |  | 6x 16 TB, RAID 5 | For Veeam Monthly Backup
5 | 36 | 2U | 192.168.17.4 | NAS-DW |  | UPS-3 | UPS-4 | Synology RS1221RP+ | 2410RXRG7VGEE | DSM 7.2.1-69057 Update 4 |  | 8x 18 TB, RAID 5 | For Veeam Daily-Weekly Backup
5 | 34 | Standalone | 192.168.5.25 | Administrator's Mac Mini |  |  | UPS-4 | Apple Mac Mini |  | macOS Catalina (v10.15.7) | 8 GB | 2x 500 GB
5 | 33 | Standalone | 192.168.5.185 | FileMaker Scripter |  |  | UPS-4 | Apple Mac Mini |  | OS X Mavericks (v10.9.5) | 8 GB | 350 GB
5 | 32 | Standalone | 192.168.5.24 | Apple Software Update Server |  |  | UPS-4 | Apple Mac Mini |  | macOS High Sierra (v10.13.6) | 4 GB | 250 GB
5 | 31 | Standalone | 192.168.5.94 | SG-POS-MACMINI2 |  |  | UPS-4 | Apple Mac Mini |  |  |  |  | POS Portal (Dashboard)
5 | 20 | Standalone | 192.168.5.41 | CLUB21MISBI | y | UPS-3 |  | O.E.M. | O.E.M. | Windows 10 Pro | 16 GB | 930 GB (C:, System) | Custom-built SQL BI PC for M3 & POS (Gideon/Chek); same PC as 192.168.5.179
5 | 19 | 1U |  | KVM Console |  | UPS-3 |  | ATEN KVM CL5708-ATA
5 | 17 | 2U | 192.168.5.38 | SGCLUB21M3IC | y | UPS-3 | UPS-4 | Lenovo 5462-IDD | 06EYZVZ | Windows Server 2012 R2 Standard | 40 GB | 270 GB (C:, System), 4 TB (D:, Data) | System x3650 M5; Hyper-V Manager for SGCLUB21SFTP
5 | 15 | 2U | 192.168.5.98 | SGCLUB21EBUDGET | y | UPS-3 | UPS-4 | Lenovo 5462-AC1 | J30M85G | Windows Server 2012 R2 Standard | 120 GB | 4 TB (B:, Backup), 270 GB (C:, System) 550 GB (D:, Data) | System x3650 M5; M3 PO Upload for merchandisers
5 | 13 | 2U | 192.168.5.39 | SGCLUB21M3BIDB | y | UPS-3 | UPS-4 | Lenovo 5462-IDB | 06GWCEF | Windows Server 2012 R2 Standard | 128 GB | 270 GB (C:, System), 3 TB (D:, Data) | System x3650 M5; Hyper-V Manager for SGCLUB21FTP1V & SGCLUB21DHCP1V DellEMC Unisphere dashboard (https://10.10.10.0) via Mgmt IP 10.10.10.3 / 4
5 | 11 | 2U | 192.168.5.31 | SGCLUB21M3BI | y | UPS-3 | UPS-4 | Lenovo 5462-D2A | J30M85M | Windows Server 2012 R2 Standard | 128 GB | 270 GB (C:, System), 550 GB (D:, Data) | System x3650 M5; Hyper-V Manager for SGCLUB21FMS2V
7 | 41 | 1U |  | FTOS 1 |  | R7-UPS1 | R7-UPS2 | Dell Force10 S55
7 | 39 | 1U |  | FTOS 2 |  | R7-UPS1 | R7-UPS2 | Dell Force10 S55
7 | 37 | 1U |  | EDW 1 |  |  | R7-UPS2 | Aruba 6000 | CN31L3J1WF
7 | 35 | 1U |  | EDW 2 |  |  | R7-UPS2 | Aruba 6000 | CN31L3J261
7 | 33 | 1U |  | Network Switch |  | R7-UPS1 |  | HP 1410-24G | CN2298L3ZN
7 | 21 | Standalone | 192.168.5.196 | DESKTOP-PI5M5D2 |  |  | R7-UPS2 | Dell Precision 3440 |  | Windows 10 Pro 21H2 |  |  | Comoclub - Extract online data and publish for Tableau online
7 | 21 | Standalone | 192.168.5.197 | comoclub-OptiPlex-5080 |  | R7-UPS1 |  | Dell Optiplex 5080 |  | Ubuntu 20.04 |  |  | Comoclub - Host Comoclub Dashboard
7 | 19 | 2U | 192.168.155.14 | CLD-DB | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740xd | DR9HNX2 | Linux 3.10.0-957.el7.x86_64
7 | 17 | 2U | 192.168.155.13 | CLD-APP | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740 | DR67NX2 | Windows Server 2016 Standard | 128 GB | 275 GB (C:, System), 6.54 TB (D:, App)
7 | 15 | 2U | 192.168.155.12 | CLP-DB | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740xd | DR87NX2 | Linux 3.10.0-957.el7.x86_64
7 | 13 | 2U | 192.168.155.11 | CLP-APP | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740 | DR6DNX2 | Windows Server 2016 Standard | 128 GB | 275 GB (C:, System), 6.54 TB (D:, App)
7 | 11 | 2U | 192.168.155.10 | CLP-SP | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740 | G6QCNX2 | Windows Server 2016 Standard | 256 GB | 550 GB (C:, System), 1.08 TB (D:, App) | Hyper-V Manager for CLP-WINPSVR, CLP-RHLPSVR & CLP-VOLAPPSVR
7 | 9 | 2U | 192.168.155.9 | CLP-BACKUP | y | R7-UPS1 | R7-UPS2 | Dell PowerEdge R740xd | G6QGNX2 | Windows Server 2016 Standard | 32 GB | 220 GB (C:, System), 275 GB (D:, App) 14.5 TB (E:, Backup)
7 | 7 | 2U |  |  |  | R7-UPS1 | R7-UPS2 | Dell EMC Data Domain | FCNBN191200050
7 | 4 | 2U | 192.168.5.82 | Rack7-UPS1 |  |  |  | Eaton 9SX 3000iR | GC38N14024 |  |  |  | Eaton UPS 3 kVA
7 | 1 | 3U | 192.168.5.83 | Rack7-UPS2 |  |  |  | Eaton 9SX 5000i | G200N32011 |  |  |  | Eaton UPS 5 kVA
10 | 42 | 1U | 172.21.27.x | M3 Backup Switch |  |  | M3-Bot | Cisco Catalyst 3650
10 | 40 | 1U | 172.21.26.x | M3 App Network Switch |  |  | M3-Bot | Cisco Catalyst 3650
10 | 38 | 1U | 172.21.25.x | M3 DB Network Switch |  |  | M3-Bot | Cisco Catalyst 3650
10 | 36 | 1U | 192.168.100.36 | M3 Production Switch |  |  | M3-Bot | Cisco Catalyst 3650
10 | 31 | 1U | 192.168.5.93 | sgposubuntu |  | M3-Top | M3-Bot | Dell EMC PowerEdge R340 |  | Ubuntu 16.04.6 LTS |  |  | Dell POS for Octopus
10 | 28 | 2U | 192.168.5.4 | Rackstation |  | M3-Top |  | Synology RS2418+ | 1880P8N893900 | DSM 6.2.1-23824 Update 1 |  | 10x 5.5 TB, RAID 5 (incl. 2 hot spares) Total capacity 36.65 TB | For M3Backup
10 | 25 | 2U | 192.168.5.33 | SGCLUB21M3ADM | y | M3-Top | M3-Bot | Lenovo 5462-AC1 | J30M85K | Windows Server 2012 R2 Standard | 32 GB | 4 TB (B:, Backup), 270 GB (C:, System) 830 GB (D:, Data) | System x3650 M5; M3 LifeCycle Manager (LCM)
10 | 23 | 2U | 192.168.5.32 | SGCLUB21M3DBAUX | y | M3-Top | M3-Bot | Lenovo 5462-AC1 | J30M85X | Windows Server 2012 R2 Standard | 128 GB | 4 TB (B:, Backup), 270 GB (C:, System) 4 TB (D:, Data), 1 TB (F:) | System x3650 M5; M3 Test DB
10 | 21 | 2U | 192.168.5.35 | SGCLUB21M3ISO | y | M3-Top | M3-Bot | Lenovo 5462-AC1 | J30M85L | Windows Server 2012 R2 Standard | 32 GB | 4 TB (B:, Backup), 270 GB (C:, System) 830 GB (D:, Data) | System x3650 M5; M3 Output Manager (MOM)
10 | 13 | 1U | 192.168.5.36 | SGCLUB21M3DB | y | M3-Top | M3-Bot | Supermicro | A263783X9808094 | Windows Server 2012 R2 Standard | 128 GB | 4 TB (B:, Backup) 420 GB (C:, 210 GB, E:, 210 GB) 7 TB (D:, 6 TB, I: 1 TB) 3.5 TB (L:, 1.75 TB, T:, 1.75 TB) | M3 Prod DB
10 | 11 | 2U | 192.168.5.40 | SGCLUB21WEB | y | M3-Top | M3-Bot | Lenovo 5462-AC1 | J30M85H | Windows Server 2012 R2 Standard | 128 GB | 4 TB (B:, Backup), 270 GB (C:, System) 540 GB (D:, Data) | System x3650 M5; M3 Portal
10 | 9 | 2U | 192.168.5.37 | SGCLUB21M3BE | y | M3-Top | M3-Bot | Lenovo 5462-AC1 | J30M85N | Windows Server 2012 R2 Standard | 36 GB | 4 TB (B:, Backup), 270 GB (C:, System) 550 GB (D:, Data) | System x3650 M5; M3 API
10 | 7 | 2U | 192.168.5.236 | SGCLUB21OLDM3DB |  |  |  | Lenovo 5462-IDB | 06GWCDM | Windows Server 2012 R2 Standard | 128 GB | 4 TB (B:, Backup), 270 GB (C:, System) 4 TB (D:, Data) | Powered off System x3650 M5; Hyper-V Manager for SOPHOSAV (shut down)
10 | 4 | 3U | 192.168.5.86 | M3UPS-Top |  |  |  | APC AP9631 | 5A1610T39750 |  |  |  | Smart-UPS RT 5000 XL
10 | 1 | 3U | 192.168.5.85 | M3UPS-Bottom |  |  |  | APC AP9537SUM | 5A1603T22129 |  |  |  | Smart-UPS SRT 5000
10-R | Floor | Standalone | 192.168.5.89 | jbaups |  |  |  | APC AP9630 | ZA1516011950 |  |  |  | Smart-UPS RT 3000 XL
2-R | 14 | Standalone |  |  |  |  | R2-UPS | RansNet CMG-1500
2-R | 5 | Standalone |  |  |  |  | R2-UPS | HP ProCurve Switch 1400-SG
2-R | 4 | Standalone |  |  |  |  | R2-UPS | Fortinet Fortigate 30B
2-R | 3 | Standalone |  |  |  |  | R2-UPS | Cisco 1841
3-R | Floor | Standalone | 192.168.5.252 | CLUB21-Project_Card |  | PUB Direct |  | Fujitsu Deskpower 2000 | J010300546 | Windows 2000 Professional SP4 | 260 KB | 37.2 GB (C:, System) | Workstation EntraPass Special Edition (Card Access System by Kantech)
3-R | 39 | Standalone |  | SingTel ONR |  |  | UPS-5 | ZTE ZXA10 F620G | EQDJJ8J06792
3-R | 38 | Standalone | 192.168.5.9 | Network Router |  |  | UPS-5 | Ransnet CMG-1500 |  |  |  |  | SSL-VPN (OpenVPN)
5-R | 31 | Standalone | 192.168.5.74 | eglobalstation | y |  | UPS-4 | Synology DS414 | 1460MEN585901 | DSM 7.1.1-42962 Update 6 |  | 3x 4 TB, Synology Hybrid RAID Vol 1 - 2x 3.63 TB with SHR (Capacity 3.63 TB) Vol 2 - 3.63 TB no RAID (Capacity 3.63 TB) | File server for eCommerce
|  |  | 192.168.5.5 | SGCLUB21DHCP1V | y |  |  | Virtual Machine |  | Windows Server 2012 Datacenter | 8 GB | 127 GB (C:, System) | Hosted on 192.168.5.39 (SGCLUB21M3BIDB); DHCP server
|  |  | 192.168.5.15 | SGCLUB21DC1 | y |  |  | Virtual Machine |  | Windows Server 2022 Standard | 8 GB | 100 GB (C:, System) | Hosted on 192.168.5.101 (SG-C21-SV-00001); Domain Controller & DNS
|  |  | 192.168.5.20 | SGCLUB21DMZDNS | y |  |  | Virtual Machine |  | Windows Server 2008 R2 Datacenter | 8 GB | 127 GB (C:, System) | Hosted on 192.168.5.38 (SGCLUB21M3IC); Sharepoint server for password change; Shut down on 23/4/2024
|  |  | 192.168.5.22 | SGCLUB21RICOH | y |  |  | Virtual Machine |  | Windows Server 2022 Standard Evaluation | 16 GB | 1 TB (C:, System) | Hosted on 192.168.5.101 (SG-C21-SV-00001); Ricoh print server
|  |  | 192.168.5.44 | SGCLUB21DC2V | y |  |  | Virtual Machine |  | Windows Server 2022 Standard | 8 GB | 126 GB (C:, System) | Hosted on 192.168.5.102 (SG-C21-SV-00004); Domain Controller, DNS & DHCP server
|  |  | 192.168.5.45 | SGCLUB21FMS2V | y |  |  | Virtual Machine |  | Windows Server 2008 R2 Datacenter | 32 GB | 300 GB (C:, System) | Hosted on 192.168.5.31 (SGCLUB21M3BI); Filemaker web
|  |  | 192.168.5.51 | SG-C21-SV-00005 | y |  |  | Virtual Machine |  | Windows Server 2022 Standard Evaluation | 8 GB | 127 GB (C:, System) | Hosted on 192.168.5.101 (SG-C21-SV-00001); Empty VM set-up
|  |  | 192.168.5.61 | SGCLUB21SFTP | y |  |  | Virtual Machine |  | Windows Server 2012 R2 Datacenter | 8 GB | 127 GB (C:, System) | Hosted on 192.168.5.38 (SGCLUB21M3IC); SFTP server
|  |  | 192.168.5.140 | SGCLUB21FTP1V | y |  |  | Virtual Machine |  | Windows Server 2008 R2 Datacenter | 8 GB | 227 GB (C:, System) | Hosted on 192.168.5.39 (SGCLUB21M3BIDB); FTP server for scan folders
|  |  | 192.168.5.178 | [9 empty] | Second IP Addr, same machine as 192.168.5.10
|  |  | 192.168.5.179 | [9 empty] | Second IP Addr, same machine as 192.168.5.41
|  |  | 192.168.5.183 | SGCLUB21DSYNC1v | y |  |  | Virtual Machine |  | Windows Server 2022 Standard | 8 GB | 80 GB (C:, System) | Hosted on 192.168.5.102 (SG-C21-SV-00004); AD Connect & Intune AD Connector
|  |  | 192.168.155.15 | CLP-WINPSVR | y |  |  | Virtual Machine |  | Windows Server 2016 Standard | 44 GB | 128 GB (C:, System), 400 GB (D:) | Hosted on 192.168.155.10 (CLP-SP)
|  |  | 192.168.155.16 | CLP-RHLPSVR |  |  |  | Virtual Machine |  | Linux 3.10.0-957.el7.x86_64 |  |  | Hosted on 192.168.155.10 (CLP-SP)
|  |  | 192.168.155.17 | CLP-VOLAPPSVR |  |  |  | Virtual Machine |  | Linux 3.10.0-957.el7.x86_64 |  |  | Hosted on 192.168.155.10 (CLP-SP)

## Cable label (hidden)
Cable Connection | Cable Labelling
Rack 2 Cisco Catalyst 3850 L3CORESW1 Port 17 | R2 L3CORESW1 P17
connected to | to
Rack 3 G700 MAIN G1 Port EXT 1 | R3 G700 MAIN G1 EXT 1
Rack 2 Cisco Catalyst 3850 L3CORESW1 Port 18 | R2 L3CORESW1 P18
connected to | to
Rack 3 G700 LSP-A G3 Port EXT 1 | R3 G700 LSP-A G3 EXT 1
Rack 2 Fortinet FortiGate 200F Port 4 | R2 FortiGate 200F P4
connected to | to
Rack 3 Cisco Catalyst 3650 L3CORESW2 Port 1 | R3 L3CORESW2 P1
Rack 7 Dell EMC PowerEdge R740 CLD-APP Port 1 | R7 CLD-APP P1
connected to | to
Rack 3 Cisco Catalyst 3650 L3CORESW2 Port 2 | R3 L3CORESW2 P2
Rack 4 Lenovo System x3650 M5 (8871-AC1) SGCLUB21BK Nie4 Port 1 | R4 SGCLUB21BK Nie4 P1
connected to | to
Rack 6 Force10 S55 FTOS Port 2/19 | R6 FTOS P2/19
Rack 5 Mac Mini FileMaker Scripter | R5 FileMaker Scripter
connected to | to
Rack 6 Force10 S55 FTOS Port 2/34 | R6 FTOS P2/34